## Learning Curve, Productivity
Ideal first attempt time (100% engagement/productivity) = |  | 20 | days
Ideal second attempt time (100% engagement/productivity) = |  | 17 | days | Learning percentage = | 85%
Engagement/productivity factor = |  | 100%
Attempt # | Time/Duration (days) Factoring in engagement/productivity
1 | 20
2 | 17
3 | 15.4583
4 | 14.45
5 | 13.7134
6 | 13.1396
7 | 12.6731
8 | 12.2825
9 | 11.9479
10 | 11.6564
11 | 11.3988
12 | 11.1686
13 | 10.961
14 | 10.7722 | Talia is working on a Task A which is on a project's critical path. She has worked on Task A for other projects in the past and this is the fifth time she is working on Task A. AssumeTalia is (and always has been) very highly motivated (engagement/productivity factor = 100%) and that she took 12 days on her first Task A attempt and 10 days on her second Task A attempt. How long will she take this time around (on her fifth attempt)?
15 | 10.5993
16 | 10.4401
17 | 10.2928
18 | 10.1558 | Now, let's assess what might have been the situation if Talia felt harrassed on the job, was unhappy, and was entertaining thoughts of quitting her position and joining another company. As a result, over the past several months, she has had challenges focusing on and devoting her full energy to her work, and her engagement/productivity factor fell to about 70% (prior to her first Task A attempt) and has stayed at that level since then. Under this scenario, how long will she take this time around (on her fifth attempt)?
19 | 10.0278
20 | 9.9079
Attempt #